## Sheet1
BIOROBOTICS PROJECT
Tasks |  |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30
|  |  | 2010-06-11 | 13/11/2010 | 20/11/2010 | 27/11/2010 | 2010-04-12 | 2010-11-12 | 18/12/2010 | 25/12/2010 | 2011-01-01 | 2011-08-01 | 15/1/2011 | 22/1/2011 | 29/1/2011 | 2011-05-02 | 2011-12-02 | 19/2/2011 | 26/2/2011 | 2011-05-03 | 2011-12-03 | 19/3/2011 | 26/3/2011 | 2011-02-04 | 2011-09-04 | 16/4/2011 | 23/4/2011 | 30/4/2011 | 2011-07-05 | 14/5/2011 | 21/5/2011 | 28/5/2011
PRESENTATIONS | bar: Week 1; Week 3 to Week 4
Collect Information | bar: Week 1; Week 3 to Week 8
Software
Kiel
MOTORS | bar: Week 3 to Week 4; Week 6
ADC | bar: Week 4 to Week 6
LCD | bar: Week 6 to Week 9
KEYPAD | bar: Week 7 to Week 8
SENSORS | bar: Week 3 to Week 9
Proteus
MOTORS | bar: Week 3 to Week 9
ADC | bar: Week 3 to Week 9
LCD
KEYPAD
SENSORS | bar: Week 3 to Week 9
Hardware
MOTOR
Stepper | bar: Week 1 to Week 7
DC motor | bar: Week 4 to Week 9
Servo motor | bar: Week 1 to Week 9
Ics
AT89c51 | bar: Week 1 to Week 9
AT89c2051 | bar: Week 5 to Week 9
ADC | bar: Week 1 to Week 9
SENSOR
photocoupler | bar: Week 1 to Week 9
temperature | bar: Week 1 to Week 9
IR sensor | bar: Week 1 to Week 9
Simple Project
fire fighting robot
soft | bar: Week 1 to Week 6
hard | bar: Week 3 to Week 7
Line Following Robot
soft | bar: Week 4 to Week 9
hard | bar: Week 4 to Week 9
ASA959
soft | bar: Week 1 to Week 9
hard | bar: Week 1 to Week 9
Build prototype components
Circuit
kiel
proteus | bar: Week 4 to Week 9
hard
Body
Modify Prototype I Design
Prototype II Assembly
Test Prototype II
Develop Production Design
Control Plans
Draft robot
Revise design
Submit project
Robot Presentation Practice
Project Presentation